## PROJ-001
PROJ-001
Phases | Key Activities | Week-1 | Week-2 | Week-3 | Week-4 | Week-5
Analysis | Requirements Gathering
Backlog Creation
AWS Platform Readiness
Foundation Block | AWS Services provisioning
Sensitive datatypes (OOTB & Custom) exploration & build
Development of Sensitive data use-cases/design
Core Feature Block | Sensitive Data Discovery & secure data isolation
Generate consolidated report on DataPatrol findings & Dashboarding
ServiceNow Integration and alerting
Validation, Deployment & Handover | Integration Testing
Documentation
Product Deployment
Handover to support
Project Team | Roles
Cloud Architect
Data Architect
Data Modeller
Sr.Developer
Cloud Engineer
Sr. Tester
Project Deliverables | Deliverables
Project Management Plan
Implementation Plan
Desing Document
Test Plan
Test Report